NovaConnect vs Microsoft Teams

Gap Analysis & Implementation Plan

Version 1.0 — September 2026

# Table of Contents

1  Executive Summary

2  Feature Comparison Matrix

3  Architecture Assessment

4  Phased Implementation Plan

5  Technical Decisions & Recommendations

6  Resource Estimate

7  Quick Wins

8  Risk Register

9  Suggested Next Steps

10  Appendix: Current NovaConnect Code Map

# 1  Executive Summary

NovaConnect is a chat-core application with teams, channels, DMs, threads, reactions, @mentions, file sharing, presence, 1:1 audio/video calls, screen sharing, meeting scheduling, calendar, and an AI assistant. It lacks the conferencing, telephony, compliance, and extensibility layers that define Microsoft Teams.

This plan prioritizes high-impact, achievable increments that move NovaConnect toward Teams parity without boiling the ocean. The full roadmap spans six phases (~214 engineering-weeks, ≈ 4–5 engineers × 12 months). Phases 1–3 (foundations + group calling + Teams parity) deliver core conferencing parity in 6–8 months with 3–4 engineers.

# 2  Feature Comparison Matrix

| Capability | NovaConnect (Current) | Microsoft Teams | Gap Severity |
| --- | --- | --- | --- |
| Teams & Channels | Public/private channels, join requests, ownership | Org-wide teams, shared channels, channel moderation | Medium |
| Direct Messages | 1:1, group DMs, add participants, preferences | Cross-org chat, message recall, sensitivity labels | Low |
| Messaging | Threads, reactions, mentions, GIFs, formatting, scheduled send, translation (configurable) | Inline reply, edit history, quoted reply, markdown, announcement posts | Medium |
| File Sharing | 15MB limit, attachment preview, channel/DM assets view | SharePoint/OneDrive integration, co-authoring, version history, 250GB+ limits | High |
| Audio/Video Calls | 1:1 WebRTC (audio, video, screen share), incoming call toast, multi-tab handling | Group calls (20+), PSTN, call queues, voicemail, call transfer, recording, live captions, background blur, together mode | Critical |
| Meetings/Conferencing | Schedule meetings (recurring, RSVP, calendar), reusable meet links, peer-to-peer rooms up to 6 | Server-sided MCU/SFU (1000+), lobby, breakout rooms, recording, transcription, whiteboard, PowerPoint Live, large gallery, registration, webinar, town hall | Critical |
| Calendar | Team events, meeting integration, month view | Exchange/Outlook sync, delegate access, meeting insights, suggested times, time zones | High |
| Presence | Online/away/busy/dnd/brb/offline, status message, auto-online | Calendar-based (in a meeting, presenting), OOF, location, duration, per-device | Medium |
| Search | Per-conversation search, 50 results, literal match | Global search (KQL), filters, message hover preview, people/files tabs, eDiscovery | High |
| Notifications | In-app activity feed, mention/DM/channel invite, desktop (opt-in), sound | Granular per-channel/chat rules, priority access, missed activity email, mobile push, banner/feed control | Medium |
| Admin/Compliance | User management, role toggle, activate/deactivate, chat reports | eDiscovery, legal hold, retention policies, DLP, info barriers, audit log, guest access controls, conditional access, naming policies, usage reports | Critical |
| Extensibility | Incoming webhook (/api/integrations), Gemini AI assistant | Apps platform (tabs, bots, messaging extensions, connectors, meeting extensions), AppSource, custom apps, Power Platform, Graph API | Critical |
| Telephony | None | Phone System, calling plans, Direct Routing, Operator Connect, voicemail, auto-attendant, call park | Critical |
| Security/Identity | Session auth, bcrypt, HTTPS/WSS, block users | MFA, Conditional Access, Azure AD join, sensitivity labels, message encryption, guest lifecycle | High |
| Accessibility | Basic semantic HTML, keyboard nav in menus | WCAG 2.1 AA, screen reader optimized, high contrast, live captions, sign language view | Medium |
| Mobile | Responsive web only | Native iOS/Android, offline sync, push, share extension, Intune MAM | High |

# 3  Architecture Assessment

## 3.1  Current Stack

Backend: Node.js/Express, Knex/PostgreSQL, Socket.IO (single-process)

Frontend: Server-rendered EJS + vanilla JS modules, Bootstrap 5, Bootstrap Icons

Real-time: Socket.IO rooms per channel/DM/user, shared Express session

Media: Peer-to-peer WebRTC (1:1 calls, 6-person mesh rooms)

Auth: Session cookies, bcrypt, no MFA/OIDC

Deployment: Single Node process, file-based sessions, local certs for HTTPS

## 3.2  Scaling Constraints

| Component | Current | Teams Requirement |
| --- | --- | --- |
| Socket.IO | Single process, in-memory rooms | Redis adapter + sticky sessions |
| WebRTC | Mesh (O(n²)), max 6 | SFU/MCU, 1000+ |
| Database | Single PG, no read replicas | Multi-region, read replicas |
| File storage | Local data/ | S3/Blob + CDN |
| Background jobs | In-process scheduler | Distributed queue (BullMQ/Redis) |
| Auth | Session cookie | OIDC/JWT + MFA |

# 4  Phased Implementation Plan

## Phase 1 — Foundations (Weeks 1–4)

Make the architecture horizontally scalable and production-hardened.

| ID | Task | Details | Effort |
| --- | --- | --- | --- |
| 1.1 | Redis-backed Socket.IO | Add @socket.io/redis-adapter, publish/subscribe across workers, sticky sessions via load balancer cookie | M |
| 1.2 | Session store → Redis | Replace session-file-store with connect-redis, shared secret via env | S |
| 1.3 | Structured logging & metrics | Pino + OpenTelemetry (traces, metrics, logs), /health already exists | S |
| 1.4 | Configuration management | Validate all env vars at startup (zod), document required/production vs dev | S |
| 1.5 | Database migrations | Replace initSchema() idempotent creates with versioned migrations (node-pg-migrate or knex migrate) | M |
| 1.6 | File storage abstraction | Introduce storage interface (local/S3), migrate upload.js, add CDN URL rewriting | M |
| 1.7 | Rate limiting & hardening | express-rate-limit on auth/api, helmet, CSP, referrer-policy, HSTS | S |
| 1.8 | CI/CD pipeline | GitHub Actions: lint, test, build Docker image, deploy to staging/prod with health checks | M |

Deliverable: Horizontally scalable Node cluster behind LB, Redis-backed sessions/sockets, observable, migratable DB, object storage.

## Phase 2 — Group Calling & Conferencing Core (Weeks 5–12)

Replace peer-to-peer mesh with an SFU; support group calls and scheduled meetings with real media.

| ID | Task | Details | Effort |
| --- | --- | --- | --- |
| 2.1 | SFU selection & integration | Recommendation: mediasoup (Node, active, used by Jitsi, Daily). Alternative: Janus, Kurento, or managed (LiveKit, Daily.co, Twilio Video). Self-hosted mediasoup gives control and no per-minute cost. | L |
| 2.2 | Signaling redesign | Extend meet-signaling.js → SFU join/leave, produce/consume tracks, simulcast, SVC, data channels for chat/whiteboard | L |
| 2.3 | Group call UI | New call panel (grid layout, active speaker, pin, raise hand, reactions, chat, participants roster, settings) | M |
| 2.4 | Meeting join flow | Lobby (admit/deny), pre-join device preview, join audio/video muted by default | M |
| 2.5 | Recording (MVP) | Server-side composition (mediasoup recorder → ffmpeg → MP4 → object storage), organizer-only, retention config | L |
| 2.6 | Screen share in groups | Present tab/window/screen as separate video track, "presentation" mode in UI | M |
| 2.7 | Breakout rooms (v2) | Organizer creates rooms, assigns participants, timer, broadcast message, close rooms | L |
| 2.8 | Live captions (v2) | Web Speech API client-side or server-side (Whisper.cpp), toggle per user | M |
| 2.9 | Together mode / Large gallery (v2) | Canvas composition on client, 7×7 grid, virtual backgrounds | M |

Milestones:

Week 6: 1:1 calls migrated to SFU (parity + reliability)

Week 9: Group calls (3–20) working end-to-end

Week 12: Scheduled meetings use SFU, recording MVP, lobby

## Phase 3 — Teams Parity Features (Weeks 13–24)

Close the functional gaps for daily collaboration.

| Area | Tasks | Effort |
| --- | --- | --- |
| Messaging | Inline reply UI, quoted reply, announcement post type, markdown shortcuts, edit history view, message recall (admin/configurable), sensitivity labels (UI + metadata) | M |
| Files | S3/Blob storage, >15MB (configurable), thumbnail generation, Office preview (Office Online Viewer / OnlyOffice), versioning, "Open in SharePoint" stub | L |
| Search | Global search endpoint (full-text via PG tsvector or Meilisearch/Typesense), KQL-ish syntax, filters (from:, in:, before:/after:, has:file), result highlighting, people/files tabs | M |
| Calendar | Exchange/Outlook sync (Graph API), delegate access, meeting insights (attendee status, conflicts), time zone picker, recurring event exceptions | L |
| Presence | Calendar-derived states (in a meeting, presenting, OOF), per-device presence, "set duration" (30m, 1h, today, this week), location | M |
| Notifications | Per-channel/chat notification rules (all/mentions/none), priority access (VIP), missed-activity email digest, mobile push (FCM/APNs via web-push) | M |
| Admin/Compliance | eDiscovery search (admin UI + export), retention policies (auto-delete), legal hold, DLP regex rules, audit log (immutable append-only table), guest invite flow with approval, naming policy enforcement | L |
| Extensibility | App manifest schema, tab iframe sandbox (CSP), bot framework (webhook + proactive), messaging extensions (compose/command), meeting extensions (side panel), AppSource-like catalog page, Graph API subset (/api/graph/*) | L |

## Phase 4 — Telephony & Enterprise Voice (Weeks 25–36)

PSTN connectivity and PBX features.

| ID | Task | Details | Effort |
| --- | --- | --- | --- |
| 4.1 | SIP gateway | Integrate Kamailio/FreeSWITCH or use Twilio/Telnyx/Plivo for PSTN termination/origination | L |
| 4.2 | Phone System | User phone numbers, call routing, voicemail (record → transcription → email/activity), call history | L |
| 4.3 | Calling plans / Direct Routing | Abstraction for multiple carriers, least-cost routing, emergency calling (E911/RAY BAUM) | L |
| 4.4 | Auto-attendant / Call queues | IVR menu, business hours, queue with music/announcements, agent opt-in/out, reporting | M |
| 4.5 | Call park, transfer, delegate | Park orbit, blind/consultative transfer, manager-delegate ring group | M |
| 4.6 | Teams-certified devices | Provisioning protocol (DHCP option 43 / XML config) for Yealink/Poly/AudioCodes | M |

## Phase 5 — Security, Identity & Governance (Weeks 37–44)

| ID | Task | Details | Effort |
| --- | --- | --- | --- |
| 5.1 | OIDC/SAML + MFA | Integrate Keycloak/Authentik or Azure AD/Entra ID, TOTP/WebAuthn, conditional access policies | L |
| 5.2 | Sensitivity labels | Label taxonomy, mandatory labeling, encryption (AIP-compatible), content marking | M |
| 5.3 | Information barriers | Segment user groups, block communication/search across segments | M |
| 5.4 | Guest lifecycle | Invitation email, redemption, access reviews, expiration, guest-specific policies | M |
| 5.5 | Audit & compliance center | Unified audit log viewer, search, export, alert rules | M |

## Phase 6 — Native Mobile & Accessibility (Weeks 45–52)

| ID | Task | Details | Effort |
| --- | --- | --- | --- |
| 6.1 | React Native / Expo app | Shared TypeScript types, API client, offline-first (WatermelonDB/Realm), push (expo-notifications) | L |
| 6.2 | Share extension | iOS/Android share sheet → post to channel/DM | S |
| 6.3 | WCAG 2.1 AA audit | axe-core CI, focus management, ARIA, color contrast, keyboard traps, live regions | M |
| 6.4 | High contrast / reduced motion | CSS media queries, theme tokens already support | S |
| 6.5 | Sign language view (meetings) | Pin interpreter video, spotlight | M |

# 5  Technical Decisions & Recommendations

| Decision | Recommendation | Rationale |
| --- | --- | --- |
| SFU | mediasoup (self-hosted) | Mature, TypeScript, used in production at scale, no per-minute cost, full control |
| Search engine | Meilisearch (embedded) or Typesense | Fast, typo-tolerant, filtered search, simpler than Elasticsearch |
| Object storage | S3-compatible (MinIO local, AWS/GCS/Azure prod) | Industry standard, CDN-friendly, multipart upload |
| Background jobs | BullMQ + Redis | Reliable, delayed/retry, priority, metrics, works with existing Redis |
| Migrations | node-pg-migrate | Pure SQL, versioned, rollback, integrates with Knex pool |
| Observability | OpenTelemetry → Tempo/Loki/Prometheus (Grafana stack) | Vendor-neutral, correlates traces/logs/metrics |
| Auth provider | Keycloak (self-hosted) or Entra ID (managed) | Standards-based, MFA, SCIM, device trust, conditional access |
| Mobile | Expo (React Native) | Single codebase, OTA updates, native modules when needed |
| Office preview | OnlyOffice Document Server (self-hosted) or Microsoft Office Online Viewer (public URLs) | Render docx/xlsx/pptx in-browser without download |

# 6  Resource Estimate (Engineering Weeks)

| Phase | Backend | Frontend | DevOps/Infra | QA | Total |
| --- | --- | --- | --- | --- | --- |
| Phase 1 Foundations | 6 | 2 | 6 | 2 | 16 |
| Phase 2 Group Calling/SFU | 18 | 10 | 4 | 6 | 38 |
| Phase 3 Teams Parity | 24 | 18 | 4 | 8 | 54 |
| Phase 4 Telephony | 20 | 8 | 6 | 6 | 40 |
| Phase 5 Security/Gov | 14 | 6 | 4 | 4 | 28 |
| Phase 6 Mobile/Access | 8 | 20 | 4 | 6 | 38 |
| Total | 90 | 64 | 28 | 32 | 214 |

≈ 4–5 engineers × 12 months for full parity. Phases 1–3 (core conferencing + parity) ≈ 6–8 months with 3–4 engineers.

# 7  Quick Wins (Do First, < 2 Weeks Each)

Redis Socket.IO adapter — unblocks horizontal scaling for real-time

Meilisearch global search — high user visibility, low backend churn

S3 storage + >15MB uploads — removes daily friction

Per-channel notification rules — top user request, small scope

Message recall (soft delete + tombstone) — safety/compliance baseline

Meeting join lobby — prevents unwanted guests, reuses signaling

OIDC login (Keycloak dev instance) — proves auth migration path

# 8  Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| SFU self-hosting operational burden | Medium | High | Start with managed (LiveKit Cloud) for dev/staging; migrate to self-hosted mediasoup when traffic justifies |
| WebRTC browser compatibility | Low | High | Test matrix (Chrome/FF/Safari/Edge, desktop/mobile); fallback to TURN relay |
| PostgreSQL full-text search scaling | Medium | Medium | Meilisearch/Typesense offloads; PG tsvector fine to ~10M messages |
| Migration from session cookies to JWT/OIDC | Medium | Medium | Dual-support period; feature flag per endpoint |
| Mobile app scope creep | High | Medium | Define MVP (chat, calls, meetings, notifications) — defer tabs/bots |
| Compliance feature creep | High | High | Build eDiscovery/retention as generic policy engine, not one-off features |

# 9  Suggested Next Steps

1. Approve Phase 1 scope — provision Redis, add adapters, migrate sessions

2. Spike SFU — 1 week: deploy mediasoup + minimal join/leave + 1:1 call parity test

3. Set up Meilisearch — index existing messages, add global search endpoint + UI

4. Create migration tooling — baseline current schema, generate first versioned migration

5. Draft OIDC integration spec — decide Keycloak vs Entra ID, map roles/claims

# 10  Appendix: Current NovaConnect Code Map (Key Files)

| Area | Files |
| --- | --- |
| Server entry | src/server.js |
| DB schema & seed | src/db.js |
| Real-time (Socket.IO) | src/realtime.js |
| 1:1 Calls | src/calls.js, public/js/calls.js |
| Meet signaling (mesh) | src/meet-signaling.js, public/js/meet-room.js |
| Meet hub (links/schedule) | src/routes/meet.js, src/routes/meetings.js, public/js/meet-hub.js |
| Chat routes | src/routes/messages.js, src/routes/dm.js, src/routes/teams.js |
| Calendar | src/routes/calendar.js |
| AI | src/routes/ai.js |
| Auth/middleware | src/middleware/auth.js |
| Workspace shell | views/workspace.ejs, public/js/workspace.js |
| Chat header (DM actions) | public/js/chat-header.js |
| Channel tools | public/js/channel-tools.js |
| Theme & density | public/css/theme-blue-cyan.css, public/css/ui-density.css, public/css/style.css |